## Log
Change Log
Change No. | Category | Priority | Description | Approval status | Estimated cost | Implementation status | Notes
1 | Product | Low | Customer wants blue button instead of green one | Approved | 200 | In work
2 | Product | High | PDF export of timesheet should be possible | Pending review | 3500 | Open
3 | Responsibilies | Critical | Form development to be done by contractor, client does not have any available resources | Approved | 12000 | Open | Can be taken over by Matt and Lisa
4 | Process | Medium | Returns handling process must be reviewed together with IT team | Open
5 | Process | Medium | How do we handle spare parts orders from EU customers? Define process | Open |  |  | Workaround available
6 | Product | High | Daily sales report to be taken over from legacy system | Pending review |  |  | Sam to provide estimate
7
8
9
10

## Priority
Low
Medium
High
Critical

## Categories
Process
Product
Responsibilies
Other

## ApprStatus
Open
Approved
Pending review
Rejected

## ImpStatus
Open
In work
Pending testing
Implemented