## GanttView
| Project name: | PROJECT NAME |  | Start Date: | 2021-01-04
| Project leader: | Sam Smith |  | Finish Date: | 2021-05-04
| Client: | Global Machines Corp. |  | Status Date: | 2021-02-17
For instructions please see Help tab. To change settings -> see Help tab | time axis 2021-01-04 to 2021-12-31
WBS Level | WBS | Task | Start | Finish | Responsible | Predecessor | Predecessor 2 | Predecessor 3 | Work Days | Cal Days | % Complete | Color | Start | Finish | Work Days | Cal Days | Days done | Remaining cal. days | time axis 2021-01-04 to 2021-12-31
1 | 1 | Planning phase | 2021-01-04 | 2021-01-14 | [8 empty] | 2021-01-04 | 2021-01-14 | 9 | 11 | 0 | 11
2 | 1.1 | Project goal definition | 2021-01-04 | 2021-01-05 | Peter Smith | [5 empty] | 75% |  | 2021-01-04 | 2021-01-05 | 2 | 2 | 1 | 1
2 | 1.2 | Create schedule | 2021-01-04 | 2021-01-08 | Lynda Caroll | [5 empty] | 25% |  | 2021-01-04 | 2021-01-08 | 5 | 5 | 1 | 4
2 | 1.3 | Create budget | 2021-01-04 | 2021-01-08 | Rick Langley | [5 empty] | 25% |  | 2021-01-04 | 2021-01-08 | 5 | 5 | 1 | 4
2 | 1.4 | Workshop planning | 2021-01-13 | 2021-01-14 | Lynda Caroll | [5 empty] | 25% |  | 2021-01-13 | 2021-01-14 | 2 | 2 | 0 | 2
2 | 1.5 | Project kickoff | 2021-01-15 |  | Peter Smith |  |  |  | 1 |  | 0% |  | 2021-01-15 | 2021-01-15 | 1 | 1 | 0 | 1
1 | 2 | Concept phase | [8 empty] | 0% |  | - | - | - | - | - | -
2 | 2.1 | Customer workshop |  |  |  | 1.5 |  |  | 3 |  | 0% |  | 2021-01-19 | 2021-01-21 | 3 | 3 | 0 | 3
2 | 2.2 | Requirement specification | 2021-01-20 | [5 empty] | 15 |  | 0% |  | 2021-01-20 | 2021-02-09 | 15 | 21 | 0 | 21
2 | 2.3 | Specification review |  |  |  | 2.2 |  |  | 7 |  | 0% |  | 2021-02-10 | 2021-02-19 | 7 | 10 | 0 | 10
2 | 2.4 | Specification sign-off |  |  |  | 2.3 |  |  | 1 |  | 0% |  | 2021-02-22 | 2021-02-22 | 1 | 1 | 0 | 1
1 | 3 | Design phase | [8 empty] | 0% |  | - | - | - | - | - | -
2 | 3.1 | Casing design |  |  |  | 2.4 |  |  | 4 |  | 0% |  | 2021-02-23 | 2021-02-26 | 4 | 4 | 0 | 4
2 | 3.2 | Mechanical design | 2021-02-23 | [5 empty] | 8 |  | 0% |  | 2021-02-23 | 2021-03-04 | 8 | 10 | 0 | 10
2 | 3.3 | Electrical design | 2021-02-23 | [5 empty] | 14 |  | 0% |  | 2021-02-23 | 2021-03-12 | 14 | 18 | 0 | 18
2 | 3.4 | Design common components |  |  |  | 3.1 | 3.2 | 3.3 | 4 |  | 0% |  | 2021-03-15 | 2021-03-18 | 4 | 4 | 0 | 4
1 | 4 | Build phase | [8 empty] | 0% |  | - | - | - | - | - | -
2 | 4.1 | Machine assembly |  |  |  | 3.4 |  |  | 20 |  | 0% |  | 2021-03-19 | 2021-04-19 | 20 | 32 | 0 | 32
2 | 4.2 | Documentation | 2021-03-19 | [5 empty] | 8 |  | 0% |  | 2021-03-19 | 2021-03-30 | 8 | 12 | 0 | 12
1 | 5 | Rollout phase | [8 empty] | 0% |  | - | - | - | - | - | -
2 | 5.1 | Machine rollout |  |  |  | 4.1 | 4.2 |  | 10 |  | 0% |  | 2021-04-20 | 2021-05-04 | 10 | 15 | 0 | 15
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
[11 empty] | 0% |  | - | - | - | - | - | -
Formulas:
Start Date: = MAX([Start Date:, row below]:E12)

## Holidays
Maintain non-working days
List any holidays or other non-working days where no tasks should be scheduled.
Date | Description | Country
2021-12-25 | Christmas
2022-12-25 | Christmas
2023-12-25 | Christmas
2024-12-25 | Christmas
2025-12-25 | Christmas
2026-12-25 | Christmas
2027-12-25 | Christmas
2028-12-25 | Christmas
2021-01-01 | New Year's Day
2022-01-01 | New Year's Day
2023-01-01 | New Year's Day
2024-01-01 | New Year's Day
2025-01-01 | New Year's Day
2026-01-01 | New Year's Day
2027-01-01 | New Year's Day
2028-01-01 | New Year's Day
2021-10-11 | Columbus Day | US
2022-10-10 | Columbus Day | US
2023-10-09 | Columbus Day | US
2024-10-14 | Columbus Day | US
2025-10-13 | Columbus Day | US
2026-10-12 | Columbus Day | US
2027-10-11 | Columbus Day | US
2028-10-09 | Columbus Day | US
2021-07-04 | Independence Day | US
2022-07-04 | Independence Day | US
2023-07-04 | Independence Day | US
2024-07-04 | Independence Day | US
2025-07-04 | Independence Day | US
2026-07-04 | Independence Day | US
2027-07-04 | Independence Day | US
2028-07-04 | Independence Day | US
2021-09-06 | Labor Day | US
2022-09-05 | Labor Day | US
2023-09-04 | Labor Day | US
2024-09-02 | Labor Day | US
2025-09-01 | Labor Day | US
2026-09-07 | Labor Day | US
2027-09-06 | Labor Day | US
2028-09-04 | Labor Day | US
2021-01-18 | M.L.King Jr. Day | US
2022-01-17 | M.L.King Jr. Day | US
2023-01-16 | M.L.King Jr. Day | US
2024-01-15 | M.L.King Jr. Day | US
2025-01-20 | M.L.King Jr. Day | US
2026-01-19 | M.L.King Jr. Day | US
2027-01-18 | M.L.King Jr. Day | US
2028-01-17 | M.L.King Jr. Day | US
2021-05-31 | Memorial Day | US
2022-05-30 | Memorial Day | US
2023-05-29 | Memorial Day | US
2024-05-27 | Memorial Day | US
2025-05-26 | Memorial Day | US
2026-05-25 | Memorial Day | US
2027-05-31 | Memorial Day | US
2028-05-29 | Memorial Day | US
2021-02-15 | Presidents Day | US
2022-02-21 | Presidents Day | US
2023-02-20 | Presidents Day | US
2024-02-19 | Presidents Day | US
2025-02-17 | Presidents Day | US
2026-02-16 | Presidents Day | US
2027-02-15 | Presidents Day | US
2028-02-21 | Presidents Day | US
2021-11-25 | Thanksgiving | US
2022-11-24 | Thanksgiving | US
2023-11-23 | Thanksgiving | US
2024-11-28 | Thanksgiving | US
2025-11-27 | Thanksgiving | US
2026-11-26 | Thanksgiving | US
2027-11-25 | Thanksgiving | US
2028-11-23 | Thanksgiving | US
2021-11-11 | Veterans Day | US
2022-11-11 | Veterans Day | US
2023-11-11 | Veterans Day | US
2024-11-11 | Veterans Day | US
2025-11-11 | Veterans Day | US
2026-11-11 | Veterans Day | US
2027-11-11 | Veterans Day | US
2028-11-11 | Veterans Day | US
2021-12-26 | Boxing Day | UK
2022-12-26 | Boxing Day | UK
2023-12-26 | Boxing Day | UK
2024-12-26 | Boxing Day | UK
2025-12-26 | Boxing Day | UK
2026-12-26 | Boxing Day | UK
2027-12-26 | Boxing Day | UK
2028-12-26 | Boxing Day | UK
2021-04-02 | Good Friday | UK
2022-04-15 | Good Friday | UK
2023-04-07 | Good Friday | UK
2024-03-29 | Good Friday | UK
2025-04-18 | Good Friday | UK
2026-04-03 | Good Friday | UK
2027-03-26 | Good Friday | UK
2028-04-14 | Good Friday | UK
2021-04-05 | Easter Monday | UK
2022-04-18 | Easter Monday | UK
2023-04-10 | Easter Monday | UK
2024-04-01 | Easter Monday | UK
2025-04-21 | Easter Monday | UK
2026-04-06 | Easter Monday | UK
2027-03-29 | Easter Monday | UK
2028-04-17 | Easter Monday | UK
2021-05-03 | Early May Bank Holiday | UK
2022-05-02 | Early May Bank Holiday | UK
2023-05-01 | Early May Bank Holiday | UK
2024-05-06 | Early May Bank Holiday | UK
2025-05-05 | Early May Bank Holiday | UK
2026-05-04 | Early May Bank Holiday | UK
2027-05-03 | Early May Bank Holiday | UK
2028-05-01 | Early May Bank Holiday | UK
2021-05-31 | Spring Bank Holiday | UK
2022-05-30 | Spring Bank Holiday | UK
2023-05-29 | Spring Bank Holiday | UK
2024-05-27 | Spring Bank Holiday | UK
2025-05-26 | Spring Bank Holiday | UK
2026-05-25 | Spring Bank Holiday | UK
2027-05-31 | Spring Bank Holiday | UK
2028-05-29 | Spring Bank Holiday | UK
2021-08-02 | Summer Bank Holiday | UK
2022-08-01 | Summer Bank Holiday | UK
2023-08-07 | Summer Bank Holiday | UK
2024-08-05 | Summer Bank Holiday | UK
2025-08-04 | Summer Bank Holiday | UK
2026-08-03 | Summer Bank Holiday | UK
2027-08-02 | Summer Bank Holiday | UK
2028-08-07 | Summer Bank Holiday | UK
2021-08-30 | Late Summer Bank Holiday | UK
2022-08-29 | Late Summer Bank Holiday | UK
2023-08-28 | Late Summer Bank Holiday | UK
2024-08-26 | Late Summer Bank Holiday | UK
2025-08-25 | Late Summer Bank Holiday | UK
2026-08-31 | Late Summer Bank Holiday | UK
2027-08-30 | Late Summer Bank Holiday | UK
2028-08-28 | Late Summer Bank Holiday | UK
Formulas:
Date = (DATE(YEAR([Date, row above])+1,10,1)+(2-1)*7)+2-WEEKDAY(DATE(YEAR([Date, row above])+1,10,1),1)+IF(2<WEEKDAY(DATE(YEAR([Date, row above])+1,10,1),1),7,0)
Date = IF(AND(YEAR([Date, row above])+1>1900,YEAR([Date, row above])+1<2199),ROUND(DATE(YEAR([Date, row above])+1,4,1)/7+MOD(19*MOD(YEAR([Date, row above])+1,19)-7,30)*0.14,0)*7-6-2,"")

## Help
Using the Gantt Scheduler for Excel
WELCOME
Thank you for purchasing the Gantt Scheduler! The Gantt Scheduler enables you to schedule smaller and medium-sized projects in Excel. You don't need to be an Excel expert to use it. All you need to know is how to perform typical steps in Excel such as adding rows or columns, copying data from one cell to another and the like. If you want to use the full potential of the Planner, and use link dependent tasks, it helps if you are familiar with using formulas in Excel.
Highlights:
■ Fast entry of tasks with automatic WBS outline numbering
■ Show tasks on the Gantt view
■ Automatic scheduling of tasks respecting holidays and weekends
■ Linking of dependent tasks
■ Assign a responsible for each task
The rows below give you an overview of the main features, and there are several options that enable you to customize the Gantt Scheduler for your needs.
Do you want to hear about our newest templates?
| If you want to be informed about our latest project templates, resources and tools, make sure you visit the Tactical Project Manager blog regularly (see link on the right) | Visit the blog
QUICK START GUIDE
■ Go to the Holidays tab and maintain the holidays for your country. The holidays are used for the automatic scheduling of tasks. The Gantt Scheduler will skip any weekends or non-working days defined in the Holidays tab and distribute tasks across the available working days.
■ Enter the planned start date of your project in cell F2 (in the Gantt view)
■ Continue by entering tasks into the task section (rows 8 and below). You can assign each task a WBS level using the drop-drown in the first column (A). Each task will then get a unique WBS ID. If you need more rows to enter tasks, simply copy an existing row further down below (Ctrl + D).
■ If you want to manually define the start and end date of a task, enter the start and finish date into columns D and E. If you want the Tracker to automatically schedule tasks, you should not enter a start / finish date for a task, but specify the estimated duration (either in work days or calendar days). Use columns J or K to specify the expected duration. (If you specify calendar days = task will also be scheduled on weekends).
■ If you use automatic scheduling (i.e. you don't enter fixed start/end dates for tasks), the Tracker will automatically determine the start and finish dates for every task (see columns N and O).
■ Use the Predecessor column (column J) to link tasks that are dependent. You simply have to reference the predecessor WBS using a formula. For example, you would enter '=B14' if you want the task with WBS in B14 to be the predecessor of the task you are currently maintaining.
PROGRESS TRACKING
■ You can maintain the progress of each task using the % Complete field
■ Tasks which are 100% completed will appear in grey
SETTING THE STATUS DATE
The status date on the Gantt view (cell F4) is used to highlight the current date on the timeline.
A red vertical line will appear next to the current date.
WEEKEND DAYS
The Gantt Scheduler allows you to specify the weekend days based on your local calendar. By default, Saturday and Sunday are weekend days, and no work will be scheduled on these days. But you can also define other days as non-working/weekend days using the entry field further down. The Tracker will then respect those non-working days in the scheduling.
If your weekends are Saturday and Sunday, no need to change anything here. If you want to set a different weekend pattern, use the input field on the right side to specify non-working days. For example, if Sunday and Monday should be weekend days, you have to enter the value "2".
For Excel gurus: In the background, the Gantt Scheduler uses the WORKDAYS.INTL and NETWORKDAYS.INTL functions to specify which days of a week should be considered weekend or non-working days. You can either use one of the predefined drop-down values (cell C47) or enter a string value. For example, the string '1000001' would mean Sunday and Monday are non-working days (1=non-working day, 0=working day).
| Weekend format: | 0000011
|  | Option | Non-Work Days
|  | 1 | Saturday, Sunday
|  | 2 | Sunday, Monday
|  | 3 | Monday, Tuesday
|  | 4 | Tuesday, Wednesday
|  | 5 | Wednesday, Thursday
|  | 6 | Thursday, Friday
|  | 7 | Friday, Saturday
|  | 11 | Sunday Only
|  | 12 | Monday Only
|  | 13 | Tuesday Only
|  | 14 | Wednesday Only
|  | 15 | Thursday Only
|  | 16 | Friday Only
|  | 17 | Saturday Only
STARTING DAY OF WEEK
In the timeline view, workweeks are separated by vertical lines. Choose the start day for a work week.
| Week starts on: | Sunday | 1
DATE FORMAT
You can choose the format in which dates are shown.
You can choose between US format (mm/dd/yyyy) and UK format (dd/mm/yyyy)
| Date format: | US-mdy
LINKING DEPENDENT TASKS
Use the Predecessor column (column G) to link tasks that are dependent. You simply have to reference the predecessor WBS using a formula. For example, you would enter '=B10' if you want the task with WBS in B10 to be the predecessor of the task you are currently maintaining (see image below):
HIGHLIGHTING TASKS DUE SOON
Tasks which are due in 7 days or less and which have a % complete of < 100%
will appear with a red finish date.
You can turn this feature on or off using the dropdown below.
| Highlight due tasks: | No
ADDING, MOVING OR DELETING TASKS
■ If you want to add more rows for additional tasks, just copy paste one of the existing and maintained rows
above to the new row. This ensures that the logic and all formulas are copied over to the new row.
■ To delete an existing task, select the entire row and choose Delete from the Excel menu.
If you're getting an error, you have to fix the formula manually, for example in case of REF errors.
■ To move a task, use cut & paste. First, select the corresponding row that you want to move and choose 'Cut'.
Next, go to a new task and choose 'Insert cut cells'. Excel will insert the moved task into a new row
just above the one you selected.
ADVANCED USERS: HOW TO ADD LAG FOR DEPENDENCIES
You may have cases where a task should start a specific amount of days after or before
another task has started or finished. This is called 'lag' and 'lead' in project scheduling.
With the Gantt Scheduler, you can link two tasks with a defined lag:
Example:
=WORKDAY.INTL(startdate,3,Weekend,Holidays)
This formula could be used to schedule task B exactly 3 working days after task A has been started (startdate).
Negative values can be used to schedule a task BEFORE a specific date.
ADVANCED USERS: HOW TO ADD LAG FOR DEPENDENCIES
To extend the timeline of the Gantt chart, just copy the last column and
paste it several times, or use the green selection handle and pull it to the right (see image).
START AND FINISH DATES FOR TOP-LEVEL TASKS
For tasks on the highest WBS level (level 1), the start and finish dates must be calculated manualy
by using the MIN() and MAX() formula. Use MIN() to calculate the start date for the entire WBS element
and MAX() to calculate the finish date for the entire WBS element:
NEED HELP?
If you have questions on how to use the Gantt Scheduler, send us a message via the following link:
https://www.tacticalprojectmanager.com/contact/