## Slide 1: LEAD-2030 IMPLEMENTATION
Project Status Update
By Joanne Smith (Project Manager)
Date: 02/26/2024

## Slide 2: Agenda
Project Snapshot
Timeline
Achievements
Current issues
Next steps
Cost Update
Notes: Adjust agenda based on current project events

## Slide 3: Project Snapshot
Description | Global implementation of LEAD efficiency program |  | 
Overall Status | Time | Budget1 | 
 | Quality | Planned | 704
 | Cost | Actual | 528
Accomplishments | - Project planning completed - Nominated HR project leader - Work contract review completed |  | 
Current Issues | - Work arrangement for customer care team unclear - Resource bottlenecks in Ops team due to parallel projects |  | 
Key Risks | - Decline in customer satisfaction due to disruption of service center |  | 
Next Steps | - Meet with union leader to discuss arrangement for service staff - Site assessment preparation - Presentation at next steering board meeting |  | 
1: in Thousand USD
Date: 02/26/2024
Notes: This page is meant to provide a quick snapshot of the current project metrics, including project health, budget and risks.

## Slide 4: Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project Preparation
Site Assessment
Concept Development
Process Review
Identify Stakeholders
Training & Rollout
Phase 1 GoLive
2024
Phase 2 Prep

## Slide 5: Achievements
Project planning completed
Budget approval by executive board
Stakeholder communication ready
Stakeholders identified
HR project leader nominated
Work contract review completed

## Slide 6: Current issues
Customer care team availability: The availability of the customer care team during the site assessment and training phase presents a challenge, as only 7 out of 12 colleagues are available. The project team will explore the feasibility of conducting an earlier site assessment and training session for the customer care team.
OPS team faces severe capacity limitations due to parallel projects. Project leadership will monitor the situation closely.

## Slide 7: Next steps
Meet with union leader regarding service staff involvement 03/10/23 PM
Site assessment preparation (questionnaire development) 03/12/23 Team
Prepare steering board meeting 03/31/23 PM
Due Date
Responsible

## Slide 8: Resource and Cost Budget
 | Effort (PD) |  |  | Cost (in thousands) |  | 
 | Plan | Actual | Delta | Plan | Actual | Delta
Initiation Phase | 35 | 28 | -7 | 45 | 42 | -3
Concept Phase | 70 | 74 | +4 | 95 | 102 | +7
Implementation Phase | 250 | 162 | -88 | 527 | 384 | -143
Closing | 45 | 0 | 0 | 37 | 0 | 0
TOTAL | 400 | 255 | - | 704 | 528 | -
Effort in person days (PD)
Notes: Provide a cost and effort breakdown by phase

## Slide 9: Cost/Effort Implementation Phase
 | Engi-neering | Design | Manu-facturing | Logistics | Marketing | Sales | TOTAL
plan | 70 | 45 | 75 | 28 | 25 | 7 | 250
actual | 46 | 38 | 57 | 15 | 4 | 2 | 162
delta | -24 | -7 | -18 | -13 | -21 | -5 | -88
EFFORT:
COST:
 | Implementation
plan | 527
actual | 384
delta | -143

## Slide 10: STAY IN TOUCH FOR MORE PM CONTENT
Hi! I’m Adrian Neumeyer, a Senior Project Manager and the Creator of Tactical Project Manager, where I teach a pragmatic and effective approach to project management.
To receive regular tips on project management and leadership, make sure to sign up for my newsletter. I send out 1-2 emails a month.
Connect with me on LinkedIn: https://www.linkedin.com/in/adrianneu/
Adrian Neumeyer