## Sheet1
Communication plan | www.tacticalprojectmanager.com
name of meeting or update | participants | purpose | frequency | type
project manager status meeting | customer and contractor project manager | review status of deliverables, alignment, project planning | weekly | physical meeting
project team meeting – core team | project manager, core project team | status update, alignment | weekly | physical meeting
project team meeting – extended team | project manager, extended project team (including infrastructure, security and migration) | status update, alignment | monthly | physical meeting
steering board meeting | steering board members | status update, decision-making on major topics, approval of extra budget | monthly | physical meeting
escalation meeting | depends on issue | alignment, resolve issues | ad hoc | physical meeting
company-wide project status update | management level L1 and above | information | monthly | email update