## checklist
Project kickoff meeting checklist
BEFORE THE MEETING | REMARKS
Plan your project | project plan must be approved
Create necessary project documentation (project timeline, budget, charter, goal definition etc.) | project documents, in particular the project charter, must be signed
Determine needed attendees | - project team members - key stakeholders - managers from customer and contractor
Sent out meeting invitation (several weeks or even months in advance) | schedule meeting in the morning if possible
Block conference room
Organize presentation equipment (A/V, beamer, whiteboard etc.)
Prepare Powerpoint slides | required slides: - project goal - project background - scope - assumptions and risks - project organization - timeline - roles and responsibilities - teamwork and organizational topics - next steps
For people unable to attend: schedule separate kickoff
30 minutes before meeting: pre meeting check | check if conference room is ready, see if audio and video equipment and internet connection are working fine
AT THE MEETING
Welcome attendees
Introduce yourself and the team
Go through slides | particularly, make sure that: - people understand at what times they're going the be involved - people understand their role and responsibility
Questions & Answers session
Close meeting
AFTER THE MEETING
Send out email with kickoff slides
Authorize team for project shared drive