## Help
© Copyright 2021 by Adrian Neumeyer
Project Budget for Excel (Monthly)
The budget template enables you to plan your project budget and track actual costs on a per-month basis.
It also allows you to calculate your costs using defined standard rates for labor and other cost items.
Key features:
- Plan project budgets
- Track actual costs
- Supports various cost types: labor, material, services, travel, equipment, other
- Perform variance analysis (plan vs. actual)
- Create cost reports
Always carefully double-check your numbers before using the calculated values in offers, bids or approvals.
Getting started
Go to the Rates tab and maintain your standard rates for labor.
The template uses the field 'Department name' to find the correct
daily rate for labor entered into the Labor effort tab.
The 'Department name' in the 'Labor effort' tab must match the 'Department name' in the 'Rates' tab!
Entering the planned labor effort
Enter any estimated work effort into the Labor effort tab (entries must be made in DAYS)
If you have correctly maintained your cost rates, you can now see labor costs
in the Labor costs tab.
Labor effort:
Labor cost:
Entering actual labor effort
To track the real days spent, use the Actual columns in the Labor effort tab
Again, you must have correctly maintained your cost rates to see the actual labor costs
in the Labor costs tab.
Actual days (in red):
Corresponding labor costs (in red):
Entering costs for material, equipment, services, travel and other items
You can also enter any project-related expenses for material, travel, equipment or other items.
Use the tabs Material, Services, Travel, Equipment and Other for this.
Costs for these categories must be entered in currency value ($ etc.) and NOT in quantities.
Example:
Creating cost reports
Use the Reporting tab to create any kind of cost report or chart.
By default, the budget template shows a cost summary for the various cost categories.
Adding additional rows
The Budget Template can be easily extended by adding extra rows.
To add more rows for additional cost items, simply select one of the existing rows,
press the right mouse button and press Insert. This will ensure that the formulae are
also copied over to the new row(s).
Make sure to double-check the summarization formula captures the entire range:
Always carefully double-check your numbers before using the calculated values in offers, bids or approvals.

## Reporting
Project Budget Reporting
| 2021 |  | 2022 |  | 2023
| Plan | Actual | Plan | Actual | Plan | Actual
Labor | 63600 | 31500 | 2800 | 700 | 0 | 0
Material | 25515 | 9600 | 100 | 90 | 0 | 0
Services | 14780 | 14780 | 0 | 0 | 0 | 0
Equipment | 0 | 0 | 0 | 0 | 0 | 0
Travel | 28280 | 28629 | 0 | 0 | 0 | 0
Other | 27 | 24 | 30 | 44 | 30 | 44
Total cost | 132202 | 84533 | 2930 | 834 | 30 | 44

## Labor effort
LABOR EFFORT (in days) |  | Enter the planned (and actual) effort in DAYS
|  | 2021 | [23 empty] | Total effort 2021 [days] |  | 2022 | [23 empty] | Total effort 2022 [days] |  | 2023 | [23 empty] | Total effort 2023 [days]
|  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Name | Department | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
Amy Fisher | Accounting | 4 | 5 | 6 | 5 | 6 | 6 | 5 |  | 3 |  | 4 |  | 1 |  | 1 |  | 3 |  | 4 |  | 1 |  | 0 |  | 38 | 16 | 2 | 1 | 2 | [21 empty] | 4 | 1 | [24 empty] | 0 | 0
John Smith | Sales | 6 | 3 | 2 | 3 | 6 | 5 | 3 |  | 5 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 |  | 1 |  | 28 | 11 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Rebecca Clark | Maintenance | 1 | 2 | 1 | 1 | 4 | 7 | 2 |  | 1 |  | 1 |  | 2 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 17 | 10 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Robert Mills | Maintenance | 3 | 3 | 6 | 6 | 3 | 2 | [18 empty] | 12 | 11 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL (days) |  | 14 | 13 | 15 | 15 | 19 | 20 | 10 | 0 | 9 | 0 | 6 | 0 | 4 | 0 | 3 | 0 | 5 | 0 | 6 | 0 | 2 | 0 | 2 | 0 | 95 | 48 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Labor cost
LABOR COSTS ($) |  | This sheet shows the labor effort in currency value. It calculates labor costs by multiplying effort from the 'Labor effort' sheet with the rates defined in the 'Rates' tab. Do not enter any data here. However, adding additional rows is fine.
|  | 2021 | [23 empty] | Total labor cost 2021 [$] |  | 2022 | [23 empty] | Total labor cost 2022 [$] |  | 2022 | [23 empty] | Total labor cost 2023 [$]
|  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Name | Department | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
Amy Fisher | Accounting | 2800 | 3500 | 4200 | 3500 | 4200 | 4200 | 3500 | 0 | 2100 | 0 | 2800 | 0 | 700 | 0 | 700 | 0 | 2100 | 0 | 2800 | 0 | 700 | 0 | 0 | 0 | 26600 | 11200 | 1400 | 700 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
John Smith | Sales | 4200 | 2100 | 1400 | 2100 | 4200 | 3500 | 2100 | 0 | 3500 | 0 | 700 | 0 | 700 | 0 | 700 | 0 | 700 | 0 | 700 | 0 | 0 | 0 | 700 | 0 | 19600 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rebecca Clark | Maintenance | 600 | 1200 | 600 | 600 | 2400 | 4200 | 1200 | 0 | 600 | 0 | 600 | 0 | 1200 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 10200 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Robert Mills | Maintenance | 1800 | 1800 | 3600 | 3600 | 1800 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL ($) |  | 9400 | 8600 | 9800 | 9800 | 12600 | 13100 | 6800 | 0 | 6200 | 0 | 4100 | 0 | 2600 | 0 | 2000 | 0 | 3400 | 0 | 4100 | 0 | 1300 | 0 | 1300 | 0 | 63600 | 31500 | 1400 | 700 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Material
MATERIAL COSTS ($) | Enter here any material cost items here
| 2021 | [23 empty] | Total material cost 2021 [$] |  | 2022 | [23 empty] | Total material cost 2022 [$] |  | 2023 | [23 empty] | Total material costs 2023 [$]
| Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Item | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
120 marble tiles | 2280 | 2200 |  |  |  |  | 7890 | 7400 | [16 empty] | 10170 | 9600 |  |  | 100 | 90 | [20 empty] | 100 | 90 | [24 empty] | 0 | 0
server hardware |  |  | 15000 | [21 empty] | 15000 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
network cables |  |  | 345 | [21 empty] | 345 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL ($) | 2280 | 2200 | 15345 | 0 | 0 | 0 | 7890 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25515 | 9600 | 0 | 0 | 100 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Equipment
EQUIPMENT COSTS ($)
| 2021 | [23 empty] | Total equipment costs 2021 [$] |  | 2022 | [23 empty] | Total equipment cost 2022 [$] |  | 2023 | [23 empty] | Total equipment cost 2023 [$]
| Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Item | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
Hammer drill | [24 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL ($) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Services
SERVICE COSTS ($) | Enter any service cost items here
| 2021 | [23 empty] | Total service costs 2021 [$] |  | 2022 | [23 empty] | Total service costs 2022 [$] |  | 2023 | [23 empty] | Total service costs 2023 [$]
| Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Item | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
Translation service EN -> CN |  |  |  |  | 14000 | 14000 | [18 empty] | 14000 | 14000 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Liability insurance | 780 | 780 | [22 empty] | 780 | 780 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL ($) | 780 | 780 | 0 | 0 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14780 | 14780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Travel
TRAVEL COST ($) | [71 empty] | Enter here any travel cost items
|  | 2021 | [23 empty] | Total travel cost 2021 [$] |  | 2022 | [23 empty] | Total travel cost 2022 [$] |  | 2023 | [23 empty] | Total travel costs 2023 [$]
|  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Item | Comment | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
Annual Sales Conference Chicago (3 people, 3 days) |  | 3600 | 3750 | [22 empty] | 3600 | 3750 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Hotel cost Sales Conf. Chicago |  | 1080 | 1089 | [22 empty] | 1080 | 1089 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Process workshop Seattle (10 attendants, 4 days) |  |  |  | 20000 | 20000 | [20 empty] | 20000 | 20000 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
Hotel cost Seattle |  |  |  | 3600 | 3790 | [20 empty] | 3600 | 3790 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[26 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL |  | 4680 | 4839 | 23600 | 23790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28280 | 28629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Other
OTHER COST ($) | Enter here any other cost items that you want to show separately.
| 2021 | [23 empty] | Total other cost 2021 [$] |  | 2022 | [23 empty] | Total other cost 2022 [$] |  | 2023 | [23 empty] | Total other cost 2023 [$]
| Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  |  |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Item | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
printer paper | [6 empty] | 27 | 24 | [16 empty] | 27 | 24 | 30 | 44 | [22 empty] | 30 | 44 | 30 | 44 | [22 empty] | 30 | 44
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
[25 empty] | 0 | 0 | [24 empty] | 0 | 0 | [24 empty] | 0 | 0
TOTAL ($) | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 24 | 30 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 44 | 30 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 44

## Rates
RATES ($)
LABOR
Department | Rate ($ / day)
Accounting | 700
Sales | 700
Maintenance | 600
EXTERNAL-Supersoft | 1100

## Sheet1 (hidden)
If you downloaded this template from any other site than tacticalprojectmanager.com, the owner of the source site has violated copyright law