## Budget
Project Budget
[10 empty] | Budget | Actual | Deviation
Project: | Machine development project | [7 empty] | Total | 41915 | 41005 | 910
Project Manager: | Erin Donley
Start Date: | 2021-02-01
Status Date: | 2021-10-15
|  |  | Labor |  | Materials |  | Equipment (variable)
WBS | Task | Owner | Hours | $/Hour | Units | $/Unit | Hours | $/Hour | Fixed Costs | Budget | Actual | Deviation
1 | Project initiation |  | 62 |  |  |  | 0 |  | 1370 | 7570 | 7635 | -65
1.1 | Create project plan | James Simmons | 30 | 100 | 0 | 0 | 0 | 0 | 0 | 3000 | 2900 | 100
1.2 | Establish project organization | James Simmons | 16 | 100 | 0 | 0 | 0 | 0 | 0 | 1600 | 1885 | -285
1.3 | Project kickoff prep & meeting | James Simmons | 10 | 100 | 0 | 0 | 0 | 0 | 1200 | 2200 | 2050 | 150
1.4 | Steering board setup and 1st meeting | Randy Hulse | 6 | 100 | 0 | 0 | 0 | 0 | 170 | 770 | 800 | -30
2 | Concept phase |  | 102 |  |  |  | 0 |  | 4500 | 13530 | 13430 | 100
2.1 | Workshop planning | Sarah Meyer | 8 | 80 | 30 | 25 | 0 | 0 | 0 | 1390 | 1380 | 10
2.2 | Customer workshop | Sarah Meyer | 24 | 85 | 0 | 0 | 0 | 0 | 4500 | 6540 | 6550 | -10
2.3.1 | Create requirement specification | Sarah M./Paul Lee | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 3200 | 3200 | 0
2.3.2 | Create system specification | Fred Whitey | 30 | 80 | 0 | 0 | 0 | 0 | 0 | 2400 | 2300 | 100
3 | Design phase |  | 163 |  |  |  | 10 |  | 3275 | 20815 | 19940 | 875
3.1 | Mechanical design | Lauren Kelsey | 50 | 100 | 0 | 0 | 0 | 0 | 275 | 5275 | 4600 | 675
3.2 | Electrical design | Todd Miller | 75 | 100 | 0 | 0 | 0 | 0 | 2000 | 9500 | 9240 | 260
3.3 | Casing design | Rebecca Taylor | 20 | 60 | 0 | 0 | 6 | 12 | 0 | 1272 | 1400 | -128
3.3.1 | External components | Sam Walton | 18 | 70 | 200 | 12 | 4 | 27 | 1000 | 4768 | 4700 | 68
4 | Summary Task | [8 empty] | 0 | 0 | 0
4.1 | Detail task | [8 empty] | 0 |  | 0
4.2 | Detail task | [8 empty] | 0 |  | 0
4.3 | Detail task | [8 empty] | 0 |  | 0
4.4 | Detail task | [8 empty] | 0 |  | 0
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Positive value indicates cost savings

## Help
Project Budget with WBS
With this budget template, you can quickly plan out budgets using different cost
categories including labor, materials and equipment as well as fixed cost items.
Key features:
- Calculate the budget amount for each WBS element
- Track actuals for each WBS element
- Immediately spot cost deviations (plan vs. actual)
- Enter the planned labor effort and calculate corresponding labor costs using standard rates
- Enter the planned material consumption and calculate material costs using standard rates
- Enter the planned equipment usage and calculate equipment costs using standard rates
Getting started
1) Enter your WBS structure into the first column
Duplicte value will appear in red
2) Add high-level or summary tasks
3) Add detail tasks and the task owners
4) Enter labor hours and rates, material units and rates, equipment hours and rates
5) Enter any fixed costs
How the Budget value is calculated
The Budget value in column K is calculated as follows:
Budget value = labor hours x rate + material units x rate + equipment hours x rate + fixed costs
Cost deviations
The template automatically calculates the cost deviation in column M:
Deviation = Budget - Actual
A positive value indicates cost savings; a negative value indicates a cost overrun.
Adding more rows
To add more rows at the bottom, just copy/paste an existing blank row below. You can also use the drag handle.
This method ensures that all formulae and conditional formatting is copied over to the new rows.
When adding rows, make sure to change the sum formula in cells K4 & L4 & M4:
so that they include your additional rows.
Totals for summary WBS elements
The totals for Budget and Actual on the summary WBS elements (in bold) are calculated
using the SUM() formula. Make sure to use this formula when adding more rows: