## Sheet1
Project Escalation Matrix
Person responsible | Role | Triggers when
Rosanne Carter | Head of IT | - server setup issues / delays - authorization issues - software licensing issues - limited availability of PCs - resource bottlenecks for IT staff
John Woodward | Head of Logistics | - delivery issues - warehouse staff unavailable - import /export issues
Sharlene Reed | Director Travel Operations | - visa issues
Eugene Hirsch | Head of Engineering | - delays of machine design - resource bottlenecks for engineering team