## Slide 1: Project status update template
Provided to you by tacticalprojectmanager.com

## Slide 2: Project status report
project name | Rollout flexible working hours at GlobalTech Inc. |  | 
overall status | time | cost (plan) | 704
 | quality |  | 
 |  | cost (actual) | 528
 | budget |  | 
accomplishments | - project planning completed - nominated HR project leader - new employee contracts created |  | 
critical issues | - work arrangement for customer care team unclear - resource bottlenecks due to parallel projects |  | 
major risks | - decline in customer satisfaction due to disruption of service center |  | 
next steps | - meet with union leader to discuss arrangement for service staff - presentation at next board meeting |  | 

## Slide 3: Project summary
 | effort (PD) |  |  | cost (in thousands) |  | 
 | plan | actual | delta | plan | actual | delta
initiation phase | 35 | 28 | -7 | 45 | 42 | -3
concept phase | 70 | 74 | +4 | 95 | 102 | +7
implementation phase | 250 | 162 | -88 | 527 | 384 | -143
closing phase | 45 | 0 | 0 | 37 | 0 | 0
TOTAL | 400 | 255 | - | 704 | 528 | -
Effort in person days (PD)

## Slide 4: Phase: Implementation phase
 | engi-neering | design | manu-facturing | logistics | marketing | sales | TOTAL
plan | 70 | 45 | 75 | 28 | 25 | 7 | 250
actual | 46 | 38 | 57 | 15 | 4 | 2 | 162
delta | -24 | -7 | -18 | -13 | -21 | -5 | -88
EFFORT:
COST:
 | implementation phase
plan | 527
actual | 384
delta | -143