## Project Gantt chart
IT System Upgrade Project | [7 empty] | Last updated: 13.01.2018 | MM/DD/YYYY
Team involved
| Process | IT | Vendor | % complete | 2017-12-01 | Jan | Feb | Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
National holidays
Local holidays
CONCEPT PHASE
Project Kick-off | X | X | X | 100%
Process workshops | X |  |  | 70%
Requirement specification | X |  |  | 20%
Workshops with vendors | X | X | X | 0%
Vendor evaluation | X | X | X | 0%
Technical concept |  | X | X | 0%
Project status meeting | X | X | X | 0%
IMPLEMENTATION PHASE
Kick-off implementation phase | X | X | X | 0%
Software implementation |  | X | X | 0%
Connection with vendor platform |  | X | X | 0%
Pre-test |  | X | X | 0%
Migration of test data |  | X |  | 0%
Functional test | X | X | X | 0%
Integration test | X | X | X | 0%
Re-test of open issues | X | X | X | 0%
Create user documentation | X |  |  | 0%
Project status meeting | X | X | X | 0%
CLOSING PHASE
Kick-off closing phase | X | X | X | 0%
End-user training | X |  |  | 0%
Data migration |  | X |  | 0%
Perform changes in live system |  | X |  | 0%
Go-Live | X | X | X | 0%
Go-Live support | X | X | X | 0%
Project status meeting | X | X | X | 0%