## risk assessment
Project risk assessment sheet
NO. | description of risk | risk category | impact | probability | overall risk value | mitigating actions | responsible | due date
|  | RR = resource risk TR = time risk BR = business / financial risk QR = quality risk | How big is the impact of the risk? 1 = low 5 = high | How likely is the risk to occur? 1 = low 5 = high | impact x probability Attention on risks with value of 16 and above. | What will be done to reduce (or eliminate) the risk? | Who will take care of the mitigating actions? | By when will the actions be implemented?
1 | Resource bottlenecks due to team members being assigned to parallel projects | RR | 4 | 4 | 16 | 1. Closely monitor progress of parallel projects. 2. Look for suitable external contractor who can support during peak phases. | John Smith | 2019-06-30
2 | Software does not fulfil customer requirements | QR | 5 | 2 | 10 | 1. Create a prototype the customer can review 2. Create specification template to document customer needs | Patrick Read | 2019-05-31
3 |  |  |  |  | 0
4 |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## categories
RR
BR
TR
QR

## values
1
2
3
4
5