## work packages
Work Package List
Item # | Area/Process | Sub-category | Description | Priority | Assigned To | Requested by | Status | Due date | Comments
WP-100 | Requirements | Requirements | Requirement specification | high | Ashley | PM | open | 2021-01-31 | Check if template needs to be updated
WP-101 | Requirements | Requirements | System concept | high | Tom | PM | open | 2021-01-31
WP-104 | Migration | Data migration | Migration concept | high | Ricky | PM | open | 2021-04-30
WP-105 | Migration | Data migration | Mapping table for customers | high | Ricky | PM | open | 2021-04-30
WP-106 | Migration | Data migration | Mapping table for vendors | medium | Ricky | PM | open | 2021-04-30
WP-107 | Software | Customization | Customization internal logic | high | Stefan | PM | open | 2021-05-31
WP-108 | Software | Customization | Customization interfaces | medium | Stefan | PM | open | 2021-05-31
WP-109 | Software | Customization | Customization user interface | low | Francois | PM | open | 2021-05-31
WP-110 | Training | User training | Training schedule for end-users | medium | Rose | PM | open | 2021-09-30
WP-111 | Training | User training | Training documentation (Powerpoint) | medium | Rose | PM | open | 2021-09-30

## priorities
low
medium
high

## status
open
in work
done