## task list
Project SAP Rollout Tire Group
No | Area | Task | Responsible | Due date | Completed on | Status | Comment
1 | PM | Organize Kick-off meeting | Project Manager | 31.10.2017 |  | open
2 | PM | Find suitable conference room | Project Manager | 05.10.2017 |  | open
3 | PM | Prepare kick-off presentation | Project Manager | 17.10.2017 |  | in work
4 | Accounting | Name project resource | John Smith | 15.10.2017 |  | done | Amanda will support
5 | Logistics | Name project resource | Marc Bellamy | 15.10.2017 |  | in work
6 | Materials Mgt. | Name project resource | Heather Stone | 15.10.2017 |  | in work
7 | PM | Finish communication plan | Project Manager | 31.10.2017 |  | open
8 | [5 empty] | open
9 | [5 empty] | open
10 | [5 empty] | open
11 | [5 empty] | open
12 | [5 empty] | open
13 | [5 empty] | open
14 | [5 empty] | open
15 | [5 empty] | open
16 | [5 empty] | open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open
open

## status
open
in work
done